## Agile Sprint Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a Developer, I want to upload or paste Python code so that the system can accept it for analysis | MUST HAVE | None | Saanvi Sahoo | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a Developer, I want syntax errors and undefined variables to be detected automatically | MUST HAVE | US-01 | Saanvi Sahoo | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a Developer, I want my code to be checked against PEP8 standards for better coding practices | MUST HAVE | US-02 | Saanvi Sahoo | 3- Completed
Sprint 3 | Sprint 3 | US-04 | As a Developer, I have learned a new framework called Reflex which is an extended framework of React and gives the flexibility to develop the backend in Python | SHOULD HAVE | US-03 | Naveen | 3- Completed
Sprint 4 | Sprint 4 | US-05 | As a Developer, I want to see before-and-after code snippets for better understanding | SHOULD HAVE | US-04 | Saanvi Sahoo | 3- Completed
Sprint 5 | Sprint 5 | US-06 | As a Developer, I want to scan a GitHub repository and analyze all its files for code quality issues | MUST HAVE | US-05 | Saanvi Sahoo | 3- Completed
Sprint 5 | Sprint 5 | US-07 | As a Developer, I want a security vulnerability scanner to detect unsafe Python code patterns such as eval() and hardcoded credentials | MUST HAVE | US-05 | Saanvi Sahoo | 3- Completed
Sprint 6 | Sprint 6 | US-08 | As a Developer, I want an AI chat assistant powered by a local LLM (Ollama / Groq) so I can ask questions about my code in natural language | SHOULD HAVE | US-06 | Saanvi Sahoo | 3- Completed
Sprint 6 | Sprint 6 | US-09 | As a Developer, I want cyclomatic complexity analysis so I can understand how maintainable my functions are | SHOULD HAVE | US-07 | Saanvi Sahoo | 3- Completed
Sprint 7 | Sprint 7 | US-10 | As a Developer, I want the application deployed on the cloud so that it is accessible from anywhere without local setup | MUST HAVE | US-08 | Saanvi Sahoo | 3- Completed