## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Saanvi Sahoo | 12/8/2025 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 12/9/2025 | Closed | Issue resolved; all unused imports now flagged correctly
2 | Saanvi Sahoo | 12/9/2025 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Integrated stricter PEP8 checks and improved formatting rules | 12/11/2025 | Closed | Style violations now displayed consistently with rule codes
3 | Saanvi Sahoo | 12/13/2025 | Control flow graph was not rendering for Python code with nested loops | Sprint 2 | Self | Logical | Fixed networkx graph generation to handle nested control structures correctly | 12/14/2025 | Closed | CFG now renders correctly for all loop and branch combinations
4 | Saanvi Sahoo | 12/16/2025 | AI chat panel user messages were displaying empty bubbles with no text | Sprint 2 | Self | UI | Replaced rx.markdown with rx.text and set explicit text colour for user bubbles | 12/17/2025 | Closed | User messages now display correctly in the chat panel
5 | Saanvi Sahoo | 12/20/2025 | Bandit security scan returned empty results for all submitted files | Sprint 3 | Self | Logical | Removed deprecated --no-recursive flag from Bandit subprocess call | 12/21/2025 | Closed | Security scan now returns correct results for all Python files
6 | Saanvi Sahoo | 1/5/2026 | Chat panel had no vertical scroll; older messages were inaccessible | Sprint 4 | Self | UI | Replaced flex scroll with position:absolute inner div using overflow-y:scroll | 1/6/2026 | Closed | Chat panel now scrolls smoothly; all messages accessible
7 | Saanvi Sahoo | 1/10/2026 | Project name 'CodeMentor AI' was inconsistent across all pages and components | Sprint 4 | Self | Standards | Used sed to replace all occurrences with 'AI Code Reviewer' across all files | 1/10/2026 | Closed | Name updated consistently across navbar, footer, prompts, and page titles